## Sheet1
Sprint ID | EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 4 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
Sprint2 | EPIC2 | Register | US2-1 | [As] Guest [I can] register as a tutor [So that] I can making a tutor activities such as create offer and next time I come back I don't have to fill my information in a form again. Acceptance Criterion 1: [Given] that user want to use their username which not exist in the system (valid) [When] user filling information in the registration process [Then] Ensure that thier can use their username with no problems. Acceptance Criterion 2: [Given] that user want to use their username which already exist in the system (invalid) [When] user filling information in the registration process [Then] ensure the system can acknowledge an error and notify user corectly. | Design and build UI/UX theme for registration form for tutor | Danupat | Develop | 5 | 5 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Build a frontend logic for registration process | Nattasit | Develop | 8 | 8 | 7 | 6 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Creat mock data and backend logic and database | Danupat | Develop | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Testing tutor registration fuction | Danupat & Nattasit | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US2-2 | [As] Guest [I can] register as a learner [So that] I can making a learner activities such as review tutor and next time I come back I don't have to fill my information in a form again. Acceptance Criterion 1: [Given] that user want to use their username which not exist in the system (valid) [When] user filling information in the registration process [Then] Ensure that thier can use their username with no problems. Acceptance Criterion 2: [Given] that user want to use their username which already exist in the system (invalid) [When] user filling information in the registration process [Then] ensure the system can acknowledge an error and notify user corectly. | Design and build UI/UX theme for registration form for tutor | Danupat | Develop | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Build a frontend logic for registration process | Nattasit | Develop | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Testing learner registration fuction | Danupat & Nattasit | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Testing control flow for all registration process | Danupat & Nattasit | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIC3 | Login | US3-1 | [As] Guest [I can] login in to my existing account [So that] I can access to my personal information and making an activities such as booking and searching in the system more quickly. Acceptance Criterion 1: [Given] that user input a correct username and password [When] user trying to login [Then] Ensure the system can regcognize and provide a correct information for user. Acceptance Criterion 2: [Given] that user input an incorrect username or password [When] user trying to login [Then] Ensure the system can regcognize and notify user for their mistake. | Design and build UI/UX theme for login page | Nithirun | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Build a frontend logic for authentication | Nattasit | Develop | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Build a frontend logic for authentication | Danupat | Develop | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Testing login process | Danupat & Nattasit | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total |  | 47 | Day 1: 47; Day 2: 41; Day 4: 35; Day 3: 32; Day 4: 25; Day 5: 18; Day 6: 8; Day 7: 0
Sprint Goal
Deliver a part of tutorS system
[6 empty] | Estimate |  | 47 | Day 1: 47; Day 2: 45; Day 4: 40; Day 3: 35; Day 4: 25; Day 5: 15; Day 6: 5; Day 7: 0