## Sheet1
Sprint ID | EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 4 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
Sprint2 | EPIC2 | Register Function | US2-1 | [As] guest [I can] register [So that] next time I come back I don't have to fill my information in form again. Acceptance Criterion 1: [Given] that user already registered and usally comeback to use our system. [When] he/she comeback [Then] Ensure that he/she can access to his/her information in the system. | Design and build UI/UX theme for registration pages. | Danupat | Develop | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design and build control flow in registration process | Nithirun | Develop | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Authentication Imprement | Nattasit | Develop | 8 | 8 | 8 | 7 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Testing | Ascharapon | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Todo | ยังไม่ select มาทำ
[7 empty] | Develop | กำลัง develop (design and code)
[7 empty] | Test | กำลัง test
[7 empty] | Done | ทำเสร็จ
[5 empty] | Total |  |  | 20 | 20 | 18 | 14 | 11 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Actual | 20 | 20 | 18 | 14 | 11 | 7 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Deliver a part of tutorS system