## Sheet1
Sprint ID | EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 4 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
Sprint1 | EPIC1 | Search Function | US1-1 | [As] Tutor, Learner and Guest [I want to] search each other with subject, location, cost, date and gender [So that] I can select the most matching and reduce matching time. Acceptance Criterion 1: [Given] that user input a correct tags which exist in the system [When] user sending a query tags to search engine [Then] ensure the search results is correct. Acceptance Criterion 2: [Given] that user input an incorrect tags which not exist in the system [When] user sending a query tags to search engine [Then] ensure the system can acknowledge an error and notify user corectly. | Design and build UI/UX theme for seach page | Danupat | Develop | 8 | 8 | 7 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Build a search engine | Nattasit | Develop | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Creat mock data and backend database | Nithirun & Danupat | Develop | 5 | 5 | 4 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Testing | Danupat & Nattasit | Develop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Todo | ยังไม่ select มาทำ
[7 empty] | Develop | กำลัง develop (design and code)
[7 empty] | Test | กำลัง test
[7 empty] | Done | ทำเสร็จ
[5 empty] | Total |  |  | 18 | 18 | 16 | 13 | 9 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Deliver a part of tutorS system
[6 empty] | Estimate |  |  | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0